## Project
Task | Owner | Timeframe/ Due Date | Status | Notes
Decide on platform/language | Stuart and Tyler | Fri night | Complete | Python, DoJo, phone gap
Build step 1 -- annoyance test prototype | Stuart and Tyler | By lunch Sat | In progress
Competitive research | Sunshine | By lunch Sat | In progress | 1 slide needed
User flow/UI for full prototype | Jason | By lunch Sat | In progress
Field/Internet testing | Phillip and Jason | After lunch -- till 5 Sat
Create presentation shell, begin business model canvas for brainstorm | Sunshine | Lunch till 6
Start building full interface (with UI) | Stuart and Tyler | Lunch till 6
Testing results review, iterations/pivots to concept and build out | Phillip | Dinner --6-7pm |  | 2 killer slides need
Continue building interface with ux | Stuart and Tyler | Dinner till go home
User testing with built out interface | Phillip and Jason | Sun morning to lunch
Adjustments to concept/interface | Team | Mid-day Sunday
Any additional quick tests | Phillip and Jason | After lunch -- till 4 Sat
Presentation wrap up and results | Sunshine | Sunday by dinner
Use case -- the types of people who would use this (ideal customer -- tell a story) |  |  | *brainstorm session
quitting smoking
diabetic
fun one -- e.g. grilling

## LSM
Idea Validation
A/B Test
Twitter, polls
Askyourtargetmarket.net
wufoo survey
poll daddy
paper polls
face to face
Problem: | Need an easy way to log data for experiments, and share results visually.
Solution: | Website/mobile app to collect data, plot, and provide results -- you just specify x and y coordinates.
Riskiest Assumption: | Push notifications will drive people crazy and they will opt out
MVP | mobile push notification/desktop pop-up that goes off every minute
Experiment hypothesis | the more frequent the notification the higher the annoyance
the longer the notifications continue the higher the annoyance
*find breaking point where people walked away
*experiment notes: solicit users who will give us 15 minutes testing the service
MVP | app prototype
ux tests:
first visit to site -- create a new experiment
choose variable (name, kind)
select frequency for notification
start
add data
not first visit to the site
select an existing experiment
add data - adjust widget, submit
view data -- view, graph
experiment complete -- if yes, share data

## Competitors
Competition
Name | url | Differentiation
Lucid Dreaming App | http://luciddreamingapp.com/android/help-how-to/get-the-data/
iTrackit — $2.99 — http://itunes.apple.com/us/app/i... | https://itunes.apple.com/us/app/itrackit-keep-track-of-stuff/id408865135?mt=8 | iTrackIt is an app to keep track of anything and everything. Appsafari.com calls it "a powerhouse of an app." Get started analysing your life's numbers today - in the app, or export them in CSV format to do with as you please :)
Dayta — now free! — http://itun.es/iFJ3Y9 | https://itunes.apple.com/us/app/dayta/id354915346?mt=8 | Dayta is a wonderful data tracking application that allows you to track literally everything about you; from your weight, to how many glasses of water you've had today, or even your kill/death ratio in Call of Duty, Dayta can track it all. FEATURES: - Create data logs that track anything about you. - Export data through email, along with a nice CSV file. - Create folders to organize your data. - Wipe a data log once you're done tracking a piece of data. - Consolidate data daily (automatically add values within a day together, useful for tracking glasses of water).
Tap Forms — $5 — http://itun.es/iFJ3Yd
Daily Tracker — $10 — http://itun.es/iFJ3Sy